## Ark1
TASKS |  |  |  |  | W1 [3.feb. - 9.feb.] | [6 empty] | W2 [10.feb. - 16.feb.] | [6 empty] | W3 [17.feb. - 23.feb.] | [6 empty] | W4 [24.feb. - 1.mar.] | [6 empty] | W5 [2.mar. - 8.mar.] | [6 empty] | W6 [9.mar. - 15.mar.] | [6 empty] | W7 [16.mar. - 22.mar.] | [6 empty] | W8 [23.mar. - 29.mar.] | [6 empty] | W9 [30.mar. - 5.apr.] | [6 empty] | W10 [6.apr. - 12.apr.]
START/FINISH: feb.3 - apr.8 2020 | Start | End | Devs | Time | M | T | W | T | F | SA | SU | M | T | W | T | F | SA | SU | M | T | W | T | F | SA | SU | M | T | W | T | F | SA | SU | M | T | W | T | F | SA | SU | M | T | W | T | F | SA | SU | M | T | W | T | F | SA | SU | M | T | W | T | F | SA | SU | M | T | W | T | F | SA | SU | M | T | W | T | F | SA | SU
PLANNING |  |  |  | 14d | bar: W1 [3.feb. - 9.feb.] M to W3 [17.feb. - 23.feb.] T
Overview & Sitemap | 2020-02-03 | 2020-02-07 | Everyone | 5d | W1 [3.feb. - 9.feb.] M: 3; W1 [3.feb. - 9.feb.] T: 4; W1 [3.feb. - 9.feb.] W: 5; W1 [3.feb. - 9.feb.] T: 6; W1 [3.feb. - 9.feb.] F: 7; W1 [3.feb. - 9.feb.] SA: Kick-off, overview work, basic sitemap, general researc, client meeting and planning
Wireframes | 2020-02-08 | 2020-02-10 | Schmith/Andersson | 2d | W1 [3.feb. - 9.feb.] SA: 8; W1 [3.feb. - 9.feb.] SU: 9; W2 [10.feb. - 16.feb.] M: 10; W2 [10.feb. - 16.feb.] T: Wireframing all the pages
Feature Breakdown & Research | 2020-02-11 | 2020-02-15 | Everyone | 5d | W2 [10.feb. - 16.feb.] T: 11; W2 [10.feb. - 16.feb.] W: 12; W2 [10.feb. - 16.feb.] T: 13; W2 [10.feb. - 16.feb.] F: 14; W2 [10.feb. - 16.feb.] SA: 15; W2 [10.feb. - 16.feb.] SU: 16; W3 [17.feb. - 23.feb.] M: Breaking down all features for development team to create
Review | 2020-02-17 | 2020-02-18 | Frode Karlsen | 2d | W3 [17.feb. - 23.feb.] M: 17; W3 [17.feb. - 23.feb.] T: 18; W3 [17.feb. - 23.feb.] W: Review of project plan before shipping off to design
DESIGN |  |  |  | 21d | bar: W3 [17.feb. - 23.feb.] W to W6 [9.mar. - 15.mar.] F
Research | 2020-02-19 | 2020-02-20 | Stacey Solomon | 2d | W3 [17.feb. - 23.feb.] W: 19; W3 [17.feb. - 23.feb.] T: 20; W3 [17.feb. - 23.feb.] F: Meeting with customer for branding touchpoints and brainstorming
Layout & Photography | 2020-02-21 | 2020-02-25 | Stacey Solomon | 4d | W3 [17.feb. - 23.feb.] F: 21; W3 [17.feb. - 23.feb.] SA: 22; W3 [17.feb. - 23.feb.] SU: 23; W4 [24.feb. - 1.mar.] M: 24; W4 [24.feb. - 1.mar.] T: 25; W4 [24.feb. - 1.mar.] W: Work on layout. Take photos for use on the website
Fonts & Colors | 2020-02-26 | 2020-02-26 | Stacey Solomon | 1d | W4 [24.feb. - 1.mar.] W: 26; W4 [24.feb. - 1.mar.] T: Fonts & Color Selection
Navigation Design | 2020-02-27 | 2020-03-02 | Stacey Solomon | 4d | W4 [24.feb. - 1.mar.] T: 27; W4 [24.feb. - 1.mar.] F: 28; W4 [24.feb. - 1.mar.] SA: 29; W4 [24.feb. - 1.mar.] SU: 1; W5 [2.mar. - 8.mar.] M: 2; W5 [2.mar. - 8.mar.] T: Nav Design
Interactive Design | 2020-03-03 | 2020-03-05 | Stacey Solomon | 3d | W5 [2.mar. - 8.mar.] T: 3; W5 [2.mar. - 8.mar.] W: 4; W5 [2.mar. - 8.mar.] T: 5; W5 [2.mar. - 8.mar.] F: Interactive Design
Promotional video | 2020-03-06 | 2020-03-13 | Stacey Solomon | 7d | [32 empty] | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | Promo: Client meeting, shoot footage, editing and implementation
DEVELOPMENT |  |  |  | 38d
Content creation & research | 2020-02-19 | 2020-03-05 | J.Sandberg/Karlsen | 14d | [16 empty] | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 1 | 2 | 3 | 4 | 5 | Client meeting to gather info, interview employees and write articles
Wholesales platform | 2020-03-06 | 2020-03-13 | Schmith/Anderss/Karlsen | 7d | [32 empty] | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | Build platform for wholesales customers, client meetings
Search option & Language tab | 2020-03-14 | 2020-03-14 | A.Schmith/T.Andersson | 1d | [40 empty] | 14 | 15 | Search option & EN Language build
Products section | 2020-03-16 | 2020-03-17 | A.Schmith/T.Andersson | 2d | [42 empty] | 16 | 17 | Products: Create list, sorted by options and ratings system
Log-in/Account Form | 2020-03-14 | 2020-03-14 | Frode Karlsen | 1d | [40 empty] | 14 | Log-in/Account Forms
FAQ Section | 2020-03-16 | 2020-03-17 | Frode Karlsen | 2d | [42 empty] | 16 | 17 | FAQ section & Client meeting
Nagivation & Footer | 2020-03-18 | 2020-03-19 | Andy Schmith | 2d | [44 empty] | 18 | 19 | Nav&Footer
Location info section | 2020-03-20 | 2020-03-20 | Andy Schmith | 1d | [46 empty] | 20 | Location info
Contact form | 2020-03-18 | 2020-03-18 | Frode Karlsen | 1d | [44 empty] | 18 | Contact form
Contact form rating system | 2020-03-21 | 2020-03-21 | A.Schmith/T.Andersson | 1d | [47 empty] | 21 | 22 | Rating system
Order form wholesales | 2020-03-19 | 2020-03-20 | Frode Karlsen | 2d | [45 empty] | 19 | 20 | Wholesales order form
Work application form | 2020-03-21 | 2020-03-21 | Frode Karlsen | 1d | [47 empty] | 21 | 22 | Work application form
Buttons | 2020-03-23 | 2020-03-23 | Andy Schmith | 1d | [49 empty] | 23 | Create call-to-action buttons
About us page | 2020-03-24 | 2020-03-26 | Schmith/Anderss/Karlsen | 3d | [50 empty] | 24 | 25 | 26 | About us: Client meetings to get core values emphasised
Employee interview section | 2020-03-27 | 2020-03-27 | Andy Schmith | 1d | [53 empty] | 27 | Employee interviews
Automated email work application | 2020-03-27 | 2020-03-27 | Thomas Andersson | 1d | [53 empty] | 27 | Automated Email System
Automated email orders form | 2020-03-28 | 2020-03-28 | Thomas Andersson | 1d | [54 empty] | 28 | 29 | Automated Email System
Automated email account creation | 2020-03-30 | 2020-03-30 | Thomas Andersson | 1d | [56 empty] | 30 | Automated Email System
Recipes Section | 2020-03-30 | 2020-03-31 | Schmith/Karlsen | 2d | [56 empty] | 30 | 31 | Client meeting, comments section, ratings
TESTING & LAUNCH |  |  |  | 10d
Bugfix | 2020-04-01 | 2020-04-03 | Schmith/Anderss/Karlsen | 3d | [58 empty] | 1 | 2 | 3 | Bugfixes
UI/UX Testing | 2020-04-01 | 2020-04-03 | Stacey Solomon | 3d | [58 empty] | 1 | 2 | 3 | UI/UX Testing
User Testing | 2020-04-04 | 2020-04-06 | A.Schmith/T.Andersson | 2d | [61 empty] | 4 | 5 | 6 | User Testing
Launch | 2020-04-07 | 2020-04-08 | Everyone | 2d | [64 empty] | 7 | 8 | Launch
[10 empty] | TEAM MEMBERS | [11 empty] | COLOR EXPLANATION
[10 empty] | Project Manager | [5 empty] | Frode Karlsen
[10 empty] | UX/UI Designer | [5 empty] | Stacey Solomon | [9 empty] | Client meetings
[10 empty] | Content Specialist | [5 empty] | Julie Sandberg
[10 empty] | Front-End Developer | [5 empty] | Andy Schmith | [9 empty] | Regular working days
[10 empty] | Back-End Developer | [5 empty] | Thomas Andersson
Off days (Sunday)